## Trang tính1
Test Plan
ID Project |  | DMS1
Project Name : |  | DMS Renovation
A. Reference
SRS |  | https://drive.google.com/file/d/1ivu1v9gglfPQ6dym1j8c1KXS_cdvrCCR/view?usp=sharing
B.Test Items
Add Defect
Attachment screen
Defect List screen
Defect View Or Edit screen
Batch Update Defect screen
Export Defect
Defect lifecycle
C. Test Scope |  | Win XP
All functions that are defined in requirement |  | Desktop
C. Test Devices
OS Version
Devices
D. Test Tools
Support tools: VMWare
F. Configuration
N/A
C. Execution
Sprint | Estimation (Hrs) | Planned Test Date |  | #TCs | Estimation (Hrs) | Planned Write Testcase Date |  | Tester | Test Strategy | Remark
|  | Start Date | End Date |  |  | Start Date | End Date
1 |  |  |  | 319 | 7 | 2022-04-05 | 2022-04-05 | Đức Trí | Manual testing: Functional testing UI | Devices Desktop (WinXP)
2 | 4 | 2022-04-12 | 2022-04-12
3 | 6 | 2022-04-19 | 2022-04-19
1 | 3 | 2022-04-12 | 2022-04-12 | 154 | 6 | 2022-04-05 | 2022-04-05 | Văn Nhật | Functional testing | Devices Desktop (WinXP)
1 | 2 | 2022-04-12 | 2022-04-12 | 90 | 6 | 2022-04-05 | 2022-04-05 | Bảo Tín | Functional testing | Devices Desktop (WinXP)
1 | 3 | 2022-04-12 | 2022-04-13 | 166 | 7 | 2022-03-29 | 2022-03-30 | Duy Thanh | Functional testing | Devices Desktop (WinXP)
2 | 3 | 2022-04-16 | 2022-04-17 | 150 | 6 | 2022-04-02 | 2022-04-03 | Duy Thanh | Functional testing | Devices Desktop (WinXP)
3 | 3 | 2022-04-18 | 2022-04-19 | 93 | 5 | 2022-04-04 | 2022-04-05 | Duy Thanh | Functional testing | Devices Desktop (WinXP)

## Trí
Defect View Or Edit screen
Planned Write Testcase Date
Sprint | Estimation (Hrs) | Times | Start Date | End Date | Work
1 | 2 | 09:00-11:00 | 2022-03-29 | 2022-03-29 | Write 150 test case
| 5 | 18:00-23:00 | 2022-03-29 | 2022-03-29 | Write 169 test case
Planned Test Date
Sprint | Estimation (Hrs) | Times | Start Date | End Date | Work
2 | 2 | 09:00-11:00 | 2022-04-12 | 2022-04-12 | Test 11 test case
| 2 | 18:00-20:00 | 2022-04-12 | 2022-04-12 | Test 10 test case
3 | 2 | 09:00-11:00 | 2022-04-19 | 2022-04-19 | Test 8 test case
| 4 | 18:00-22:00 | 2022-04-19 | 2022-04-19 | Test 24 test case

## Thanh
Tester | Buì Duy Thanh
Sprint | Estimation (Hrs) | Times | Start Date | End Date | Work | Estimation (Hrs) | Times | Start Date | End Date | Work
1 | 2 | 09:00-11:00 | 2022-03-29 | 2022-03-29 | Write 46 test case | 1 | 09:00-11:00 | 2022-04-12 | 2022-04-12 | Test 46 test case
| 2 | 10:00-12:00 | 2022-03-30 | 2022-03-30 | Write 55 test case |  | 10:00-12:00 | 2022-04-13 | 2022-04-13 | Test 55 test case
| 3 | 15:00-18:00 |  |  | Write 65 test case |  | 15:00-18:00 |  |  | Test 65 test case
2 | 2 | 09:00-11:00 | 2022-04-02 | 2022-04-02 | Write 50 test case | 2 | 09:00-11:00 | 2022-04-16 | 2022-04-16 | Test 50 test case
| 2 | 10:00-12:00 | 2022-04-03 | 2022-04-03 | Write 50 test case |  | 10:00-12:00 | 2022-04-17 | 2022-04-17 | Test 50 test case
| 2 | 15:00-17:00 |  |  | Write 50 test case |  | 15:00-17:00 |  |  | Test 50 test case
3 | 2 | 09:00-11:00 | 2022-04-04 | 2022-04-04 | Write 35 test case | 3 | 09:00-11:00 | 2022-04-18 | 2022-04-18 | Test 35 test case
| 1 | 16:00-17:00 |  |  | Write 20 test case |  | 16:00-17:00 |  |  | Test 20 test case
| 2 | 09:00-11:00 | 2022-04-05 | 2022-04-05 | Write 38 test case |  | 09:00-11:00 | 2022-04-19 | 2022-04-19 | Test 38 test case

## Nhật
individual test plan
Week | start times | end times | number of test cases | completion time (Hour) | implementation content | Note
7 | 2022-04-05 | 2022-04-05 | 98 | 6 | execute test cases of "Filter" part | -make test case predictions to do - Read and complete the materials first SRS
8 | 2022-04-12 | 2022-04-12 | 154 | 8 | execute test cases of "Filter", "Paging area" and "Defects listing area" | - complete test cases - There is a software bug so I can't test the product yet
9 | 2022-04-19 | 2022-04-19 | 154 | 4 | process of testing test cases | - process of testing test cases - Prepare for the presentation

## Tín
Test plan
Week | Start times | End times | Number of test cases | Completion time (Hour) | Implementation content | Note
7 | 2022-04-05 | 2022-04-05 | 60 | 6 | Write test cases of Batch Update Defect screen and Export Defect To Excel File | - Read the SRS document that describes the function of Batch Update Defect screen and Export Defect To Excel File - Make predictions about possible cases of the function - Complete 90 test cases
8 | 2022-04-12 | 2022-04-12 | 90 | 6 | Functional testing of Batch Update Defect screen | - Test completed 30% of the functions
9 | 2022-04-19 | 2022-04-19 | 90 | 6 | Functional testing of Batch Update Defect screen and Export Defect To Excel File | - Test completed 100% of the functions - Complete the test plan table