## Sheet1
Test plan
Week | Start times | End times | Number of test cases | Completion time (Hour) | Implementation content | Note
7 | 2022-04-05 | 2022-04-05 | 60 | 6 | Write test cases of Batch Update Defect screen and Export Defect To Excel File | - Read the SRS document that describes the function of Batch Update Defect screen and Export Defect To Excel File - Make predictions about possible cases of the function - Complete 90 test cases
8 | 2022-04-12 | 2022-04-12 | 90 | 6 | Functional testing of Batch Update Defect screen | - Test completed 30% of the functions
9 | 2022-04-19 | 2022-04-19 | 90 | 6 | Functional testing of Batch Update Defect screen and Export Defect To Excel File | - Test completed 100% of the functions - Complete the test plan table